## Sheet1
Fiber Project Gantt Chart
Project Organization
Project Manager
Task | Weeks Since Start | Weeks to complete
Planning
Communication Needs | 0 | 4
Establish Responsibility | 0 | 2
Approve Project | 4 | 4
Funding | 4 | 8
Bidding Contracting | 6 | 6
Design
Establish Route | 4 | 4
Rights of Way/Permits | 6 | 6
Cable Plant Design | 4 | 8
Structures/hardware | 6 | 8
Choose Components | 8 | 6
Create Documentation | 4 | 24
Installation
Procurement | 10 | 6
Construction | 12 | 6
Cable Plant Installation | 15 | 10
Splicing | 16 | 10
Testing | 18 | 10
Documentation | 4 | 24
Acceptance | 28 | 4
Operation
Communications | 28 | 36
Restoration Planning | 20 | 28
Reference: https://support.microsoft.com/en-us/office/present-your-data-in-a-gantt-chart-in-excel-f8910ab4-ceda-4521-8207-f0fb34d9e2b6